## Slide 1: Education Innovation and Research (EIR) Expansion selection criteria and scoring
March 2018
Notes: In this informational recording we’re going to provide an overview of the selection criteria for the Expansion competition, the points that are assigned to each selection criterion, and a brief overview of the review process.

## Slide 2
Expansion Selection Criteria | 
Criterion | Points
Significance | 10
B. Strategy to Scale | 35
C. Quality of Project Design and Management Plan | 35
D. Quality of the Project Evaluation | 20

## Slide 3: A. Significance (10 pts)
The magnitude or severity of the problem to be addressed by the proposed project.
The national significance of the proposed project.
The extent to which the proposed project represents an exceptional approach to the priority or priorities established for the competition.
Expansion

## Slide 4: B. Strategy to Scale (35 pts)
The extent to which the applicant demonstrates there is unmet demand for the process, product, strategy, or practice that will enable the applicant to reach the level of scale that is proposed in the application.
The extent to which the applicant identifies a specific strategy or strategies that address a particular barrier or barriers that prevented the applicant, in the past, from reaching the level of scale that is proposed in the application.
The extent to which the results of the proposed project are to be disseminated in ways that will enable others to use the information or strategies.
Expansion
Notes: The second Expansion selection criterion is strategy to scale, worth 30 points
Read slide
Please also keep in mind that it is expected that grantees are encouraged to scale their practices to a national level, which is defined in the notice inviting applications.

## Slide 5: What Have We Learned About Scaling?
See Investing in Innovation (i3) white paper at:
https://i3community.ed.gov/insights-discoveries/2207
Topics Covered:
Using multiple methods to establish buy-in;
Building a regional and national infrastructure;
Adapting practices based on evidence; and
Planning for sustainability from day one.
Notes: When thinking about scaling, it may help you to look at this white paper that was produced last year. Based on interviews with Validation and Scale-up project directors of the Investing in Innovation (i3) Program, the predecessor program to EIR, it shares some general lessons learned. We won’t talk about them now, but there are four primary topics covered.

## Slide 6: C. Quality of Project Design and Management Plan (35 pts)
The extent to which the goals, objectives, and outcomes to be achieved by the proposed project are clearly specified and measurable.
The adequacy of the management plan to achieve the objectives of the proposed project on time and within budget, including clearly defined responsibilities, timelines, and milestones for accomplishing project tasks.
The adequacy of procedures for ensuring feedback and continuous improvement in the operation of the proposed project.
The extent to which the applicant demonstrates that it has the resources to operate the project beyond the length of the grant, including a multi-year financial and operating model and accompanying plan; the demonstrated commitment of any partners; evidence of broad support from stakeholders (e.g., State educational agencies, teachers' unions) critical to the project's long-term success; or more than one of these types of evidence.
Expansion
Notes: Read slide

## Slide 7: Management Plan
Goal(s): A broad statement(s) of what the project intends to accomplish. What do you hope to accomplish by implementing your project?
Objective(s): A concrete attainment that can be achieved by following a number of steps. What is your project doing to support the overall program goal(s)? Are your objectives SMART (Specific, Measurable, Achievable, Relevant, and Time-bound)?
Performance Measures: A measurable or observable indicator to assess how well objectives are being met. How will you measure the success of your project?
Activities: Day to day pieces that must be completed to signal that the grant is on track.
Timeline (Start/End Dates): Provide some timeline that will allow task monitoring.
Responsible Personnel: Who will be carrying out those activities?
Elements To Consider
Notes: In order to respond to the 2nd factor under Selection Criterion C, you need to create a project management plan. Here are some key components of a typical well-designed management plan. You may find it helpful to use this format – or something similar.
Such a management plan could include…..
Read slide
In the next slide, we’ll show you an example of what such a management plan would look like.

## Slide 8: Management Plan
Example
Goals | Objectives | Measures | Activities | Start Date | End Date | Responsible Personnel | Status | Notes
Goal 1: Increase involvement of Smith Elementary School families in their students’ education. | Objective 1.1: Logins on the Smith Elementary School Online Parent Training System will increase 25% from baseline to the end of the grant. | Performance Measure 1.1a: Parents reporting in an annual survey knowing about the Online Parent Training System. Performance Measure 1.1b: Number of logins per year. | Activity 1.1.1: Administer parent survey to get baseline data. | 9/1/2016 | 9/15/2016 | Evaluation Team | Not Begun | 
 |  |  | Activity 1.1.2: Create a pamphlet for parents that describes how to access and use the Parent Portal. | 3/1/2016 | 3/15/2016 | Project Director | Completed | 
 |  |  | Activity 1.1.3: Distribute pamphlet during school-wide events and parent-teacher conferences. | 9/15/2016 | 12/1/2016 | Project Coordinator | Not Begun | 
 |  |  | Activity 1.1.4: Design a training for parents on using the Parent Portal | 2/1/2016 | 3/1/2016 | Project Director | Completed | 
 |  |  | Activity 1.1.5: Organize a focus group on the Parent Portal to gather parent feedback. | 11/15/2016 | 12/1/2016 | Evaluation Team | Not Begun | 
 |  |  | Activity 1.1.6: Deliver Parent Portal trainings. | 9/15/2016 | 12/1/2016 | Project Director & Project Coordinator | In Progress | Scheduled for 10/1 and 11/1.
 |  |  | Activity 1.1.7: Administer parent survey. | 5/1/2017 | 6/1/2017 | Evaluation Team | Not Begun | 
 |  |  | Activity 1.1.8: Collect monthly reports on parent logins. | 10/1/2016 | 12/1/2016 | Data Director | In Progress | 
 | Objective 1.2: The percentage of students with parents regularly engaging with the school will increase by 5% every school year. | Performance Measure 1.2a: Percentage of students that have at least 1 parent/guardian attend 1 parent-teacher conference per school year. Performance Measure 1.2b: Average parent attendance at school-wide events every school year. | Activity 1.2.1 |  |  |  |  | 
 |  |  | Activity 1.2.2 |  |  |  |  | 
 |  |  | Activity 1.2.3 |  |  |  |  | 
Notes: Here’s what a sample management plan might look like.
It wouldn’t be unusual for a management plan to take up several pages of a project narrative, but it’s up to you to decide the length and level of detail that would best communicate your plan to reviewers.

## Slide 9: D. Quality of Project Evaluation (20 pts)
The extent to which the methods of evaluation will, if well implemented, produce evidence about the project's effectiveness that would meet the What Works Clearinghouse standards without reservations as described in the What Works Clearinghouse Handbook (as defined in the notice).
The extent to which the evaluation will provide guidance about effective strategies suitable for replication or testing in other settings.
The extent to which the methods of evaluation will provide valid and reliable performance data on relevant outcomes.
The extent to which the evaluation plan clearly articulates the key project components, mediators, and outcomes, as well as a measurable threshold for acceptable implementation.
Expansion
Notes: Read slide

## Slide 10: Evaluation Expectations
Must be an independent evaluation.
Design must have potential to meet What Works Clearinghouse standards without reservations.
Encouraged to examine cost-effectiveness of practices.
Encouraged to describe how the grant’s scaling strategy will be assessed.
Should be mindful of the performance measure to examine cost-effectiveness of practices.
Expansion
Notes: Read slide

## Slide 11: Technical Assistance Resources on Evaluation
WWC Procedures and Standards Handbooks: https://ies.ed.gov/ncee/wwc/Handbooks
“Technical Assistance Materials for Conducting Rigorous Impact Evaluations”: http://ies.ed.gov/ncee/projects/evaluationTA.asp
IES/NCEE Technical Methods papers: http://ies.ed.gov/ncee/tech_methods/
In addition, applicants may view one optional webinar recording that were hosted by the Institute of Education Sciences:
  Strategies for designing and executing experimental studies that meet What Works Clearinghouse evidence standards without reservations: http://ies.ed.gov/ncee/wwc/Multimedia.aspx?sid=18
Notes: Here are some helpful resources that have been put together by the Department’s Institute of Education Sciences, (IES) that you may wish to consult in planning your project evaluation. It’s particularly important that you become familiar with the first of these, the What Works Clearinghouse Procedures and Standards Handbooks, not only to make sure your evaluation meets What Works Clearinghouse standards, but also because the handbook will help you to understand the EIR evidence requirements.

## Slide 12: What is a Logic Model?
Logic model (also known as a theory of action) means a reasonable conceptual framework that identifies key components of the proposed project (i.e., the active “ingredients” that are hypothesized to be critical to achieving the relevant outcomes) and describes the theoretical and operational relationships among the key components and outcomes.
Notes: Although you are not required to develop a logic model, it may be helpful to you to include one in your application. A logic model provides a conceptual framework for identifying the key components of your project and the relationships between them and your intended goals, objectives, and outcomes.
Going through the exercise of creating one may help you to better prepare your responses to the selection criteria, especially C: “Quality of Project Design and Management Plan,” which looks at your goals, objectives, and outcomes; and criterion D: “Quality of the Evaluation.”

## Slide 13: Sample Logic Model
Source: REL Pacific – see link on next slide.
Notes: Here is a sample logic model. If you look around at various sources, you’ll see that logic models vary from one another, and we do not require any particular format. However, this one makes sense because it shows clearly the logical relationship between the resources you have available and the activities you’ll be conducting (i.e. the inputs) and the expected outcomes of the project. This example includes inputs; activities; outputs; and short, mid, and long-term outcomes.

## Slide 14: LOGIC MODEL Resources
Education Logic Model (ELM) Application (REL Pacific)
  http://relpacific.mcrel.org/resources/elm-app/
Logic models: A tool for effective program planning, collaboration, and monitoring (REL Pacific)
  https://ies.ed.gov/ncee/edlabs/regions/pacific/pdf/REL_2014025.pdf
Logic models: A tool for designing and monitoring program evaluations (REL Pacific)
  https://ies.ed.gov/ncee/edlabs/regions/pacific/pdf/REL_2014007.pdf
Logic models for program design, implementation, and evaluation: Workshop toolkit (REL Northeast and Islands)
  https://ies.ed.gov/ncee/edlabs/regions/northeast/pdf/REL_2015057.pdf
Notes: The Regional Educational Laboratories have developed a number of resources that you can use to help you produce a logic model of your own. These are useful because they can walk you through the process of creating a logic model and show you some examples along the way.

## Slide 15: Suggestions for Selecting an Evaluator
Is the evaluator closely familiar with What Works Clearinghouse standards?
Has the evaluator conducted evaluations using a variety of designs and methodologies? Has the evaluator published?
Does the evaluator have a team of qualified individuals?
Is the evaluator independent?
Does the evaluator have strategies for recruiting control sites and experience working with districts to gain appropriate consents and to share data
Does the evaluator have experience managing data records and protecting student privacy?
Notes: As you can surely see by now, the independent evaluation is a critical part of a successful EIR project, so you need to find an evaluator that is experienced and ably qualified to conduct an evaluation that will meet What Works Clearinghouse standards.
Sometimes, individuals call themselves educational evaluators but don’t really have the background to conduct rigorous evaluation research. You need to watch out for that. So here – and in the next slide are some questions that you might want to discuss with an evaluation candidates that you identify.
Read slide

## Slide 16: Suggestions for Selecting an Evaluator (2)
Is your evaluator familiar with the literature in the area in which you’re working?
Do you see eye to eye on the goals of the evaluation, and would you have a good working relationship?
Have you talked about what might happen to the design and/or the budget if things do not go as planned?
  Problems with recruitment
  Problems with attrition
  Delays or changes to the program
Are your expected deliverables clearly defined?
Have you clearly defined responsibilities of program staff vs. evaluators, or internal vs. independent evaluators?
Notes: Read slide

## Slide 17: Overview of Expansion Review Process
Applications Sorted and Placed in Panels by Absolute Priority 2 (Field-Initiated) or Absolute Priority 3 (STEM)
Each Application is Scored Against Selection Criteria
Panel Review
  3 Peer Reviewers Review and Score Selection Criteria A, B, and C (80 points possible)
  2 “Evaluation” Reviewers Review and Score Selection Criterion D (20 points possible)
  All 5 reviewers meet to discuss the applications together
  Final Score = Average Score on Selection Criteria A, B, C + Average Score on Selection Criterion D (100 pts. Possible)
Notes: Read slide

## Slide 18: Recommendations For organizing your application
We recommend that you organize and sequence your application narrative using the selection criteria.
Within each criterion, make sure that you include a direct response to each of the factors under that selection criterion (we’ll show you these in upcoming slides).
Reviewers will be instructed that they may use material from anywhere in the application, including the appendices, to score and evaluate each criterion, but they will have an easier job if each section of your narrative is clear, well-organized, and complete – and doesn’t require them to search for information.
When appropriate, use language from the selection criteria to help guide reviewers (For example, “This project will be nationally significant because…” or “This project represents an exceptional response to the Absolute Priority because…”
Notes: Let’s start with a few general recommendations for writing your application.
Read slide

## Slide 19: Education Innovation and Research (EIR) Expansion selection criteria and scoring
March 2018
Notes: That concludes our informational recording on selection criteria and scoring for the EIR Expansion Competition. We hope that you have found it useful, and if you have additional questions, we encourage you to read the notice inviting applications.